## Slide 1
ERP TRANSFORMATION STRATEGY
Phasing, Scope & Data Continuity Recommendations
Alpha Manufacturing Group
Prepared by Rabbi Perez Kwakoa Asiedu, Digital Transformation Project Manager
18th July, 2026

## Slide 2
The Problem
A fragmented, 20-year-old application landscape
80%
of custom orders experienced margin erosion last year
Driven by unreliable labor tracking and no trustworthy contribution margin view.
Core ERP
(Finance, MRP,
Procurement)
~80 users
Engineering
System
(BOM / ECN)
Cloud CRM
(unintegrated)
HRIS / Payroll
(siloed)
fragile nightly sync
2
Excel spreadsheets manually bridge the gaps between all four systems — introducing data-entry risk and no single source of truth.

## Slide 3
Key Objectives
What the transformation must achieve by go-live
1
Reduce the 80% margin erosion rate
Restore BOM accuracy and reliable order costing.
2
Establish reliable labor tracking
Deliver a trustworthy, comprehensive contribution margin view.
3
Eliminate BOM/ECN sync failures
Remove the root cause of current manufacturing delays.
4
Rationalize the application landscape
Strengthen data governance across Finance, Manufacturing, Procurement, CRM, and HRIS.
5
Deliver within 12 months
No disruption to day-to-day operations.
3

## Slide 4
Phasing Roadmap
Function-first sequencing over a 12-month program
1
Manufacturing/MRP
+ Finance Foundation
Chart of Accounts, General Ledger, Cost Accounting: fixes fragile BOM/ECN sync at its root.
2
Procurement
Source against trustworthy BOM and cost data instead of fragmented spreadsheets.
3
Budgeting / Reporting
/ BI Layer
Ships once Manufacturing, Finance, and Procurement data is proven stable.
4
Full AP/AR +
Financial Close/Consolidation
Built out once the cost/reporting foundation is proven; legacy runs in parallel until ready.
4

## Slide 5
Location Sequencing
Prove it at one site before scaling to all five
STEP 1
Lowest-Risk
Pilot Site
Prove feasibility safely; surface issues before they affect the wider business.
If validated
STEP 2 — Remaining 4 Locations
Site 2
Site 3
Site 4
Site 5
Deployment halts immediately if the pilot reveals unresolved issues fixes come before further rollout.
5

## Slide 6
Top Risks & Mitigations
Risk | Mitigation
BOM/data migration integrity | BOM data from the legacy ERP system will be thoroughly analyzed and cleaned. So only clean data is sent to the new system.
Parallel-run complexity | Set a strict deadline for how long the two systems will be running in parallel so it doesn’t end up being permanent. There should also be regular check-ins on both systems to ensure they are up-to-date.
Scope creep from customization | Change Control Board approves only requests with justified business impact.
User adoption of the new system | Structured training and phased rollout to build confidence.
Multi-entity / 5-site complexity | Validate the data model at the pilot site before scaling further.
6

## Slide 7
Day-1 Scope
What goes live immediately vs. what deliberately waits
GO-LIVE DAY 1
✓
Chart of Accounts / General Ledger
✓
BOM/ECN accuracy (Manufacturing/MRP)
✓
Procurement sourcing
BOM/ECN accuracy is non-negotiable because without it, manufacturing cannot reliably know what to build, at what cost.
DEFERRED TO LATER PHASES
→
Full AP automation
→
CRM integration
→
HRIS/Payroll integration
→
BI/reporting dashboards
Both CRM and HRIS/Payroll already run independently so deferring integration introduces no operational risk.
7

## Slide 8
Data & Reporting Continuity
Protecting visibility and trust throughout the transition
1
Migration Exclusions
Only open/active records migrate live. Closed records stay accessible via a read-only legacy archive preserving audit access without slowing the timeline.
2
Reporting Bridge
AMG will maintain a temporary reporting bridge that will pull data from the both ERP systems so the exectives always have something reliable to look at. A simple excel sheet will be used during this transition period for reporting which will be manually maintained by a worker until BI layer is ready.
3
Month-End Parallel Close
At least one full close cycle runs in both systems simultaneously and is reconciled before the new system is trusted as the system of record.
8

## Slide 9
Recommendation
We recommend the Executive Team approve this phased approach enabling the program to proceed toward the 12-month go-live target while protecting day-to-day operations and restoring the margin transparency the Board has requested.